CPT Pharma (Pty) Ltd

Computerised System Validation

Project Plan

Capalyst QMS

| Field | Value |
| --- | --- |
| Document Number | CPT-VL-ISVP-PP Capalyst-001 |
| Version | 1.0 |
| Status | Approved |
| Date | 2026-06-01 |
| System | Capalyst — Quality Management System |
| Company | CPT Pharma (Pty) Ltd |
| Prepared by | Validation Team |
| Classification | Confidential |

# 1. Introduction

This Project Plan defines the organisation, approach, schedule, and deliverables for the Computerised System Validation (CSV) of the Capalyst Quality Management System (QMS) at CPT Pharma (Pty) Ltd. The document serves as the master reference for all validation activities performed in accordance with EU GMP Annex 11 and 21 CFR Part 11.

## 1.1 Purpose

To establish a structured and compliant framework for validating the Capalyst QMS, ensuring that the system reliably performs its intended functions in the GxP-regulated environment of CPT Pharma.

## 1.2 Scope

The validation covers the following Capalyst QMS modules:

- Deviations — recording, investigation, root cause, CAPA linkage, and QA closure

- CAPA — corrective and preventive action with efficacy review workflow

- Change Control — multi-stage approval workflow (HR, SC, Expert, QA)

- Risk Assessment — FMEA-based risk assessment per ICH Q9 / SOPPQA016 v05

- User Administration — role-based access control (Admin, QA, User)

- Dashboard — KPI summaries and trend analytics

## 1.3 Exclusions

The following are out of scope for this validation exercise:

- Third-party infrastructure components not maintained by CPT Pharma (cloud hosting platform internals)

- Disaster recovery testing of the hosting provider's infrastructure

# 2. Business Context

CPT Pharma (Pty) Ltd operates in a GxP-regulated environment and is required to maintain validated computerised systems for quality-related processes. The Capalyst QMS replaces manual (paper-based) processes for deviation management, CAPA tracking, change control, and risk assessment. The system supports regulatory compliance obligations under South African pharmaceutical regulations aligned with EU GMP and PIC/S guidelines.

# 3. Project Organisation

## 3.1 Roles and Responsibilities

| Role | Responsibility | Name / Function |
| --- | --- | --- |
| Project Manager (PM) | Overall project coordination, schedule, and resource management | TBD — QA Manager |
| Validation Expert (VE) | Lead validation activities, author validation documents, coordinate testing | TBD — Validation Specialist |
| System Owner (SO) | Business accountability for the Capalyst QMS; approves validation deliverables | Hannes van der Berg (QA Admin) |
| Business Quality Representative (BQR) | QA oversight, approves test scripts, reviews anomalies | Monique Leblanc (QA) |
| Infrastructure Expert (IE) | Technical architecture, installation, and environment qualification | TBD — IT / Systems Administrator |
| Project Technical Coordinator (PTC) | Technical liaison, manages configuration and deployment | TBD — Technical Lead |
| End User Representative | User acceptance testing, user requirements sign-off | Yoshika Tanaka (User) |

# 4. Project Approach

## 4.1 Validation Strategy

CPT Pharma adopts a risk-based validation approach consistent with GAMP 5 (Second Edition) guidelines. The Capalyst QMS is classified as a Category 4 configured software product. Validation effort is proportionate to the GxP risk and criticality of each system function.

## 4.2 Validation Lifecycle

| Phase | Document / Activity | Reference |
| --- | --- | --- |
| Planning | Project Plan, System Criticality Assessment, Validation Plan | CPT-VL-ISVP-PP / SCA / VP |
| Specification | User Requirements Specification, Architecture Specification | CPT-VL-ISVP-UR / ArS |
| Verification — IQ | Installation Qualification, Infrastructure & Application Operations Manual | CPT-VL-ISVP-IQ / IAOM |
| Verification — OQ/PQ | Test Scripts, Test Report, Database Comparison | CPT-VL-ISVP-TR / DBC |
| Closure | Authorization for Use, Validation Report | CPT-VL-ISVP-AFU / VR |

## 4.3 Testing Approach

- Functional testing covering all user requirements defined in CPT-VL-ISVP-UR

- Role-based access control testing for Admin, QA, and User roles

- Workflow state-transition testing for all four process modules

- Negative testing (invalid inputs, unauthorised actions)

- Audit trail verification for all GxP-critical data fields

- 21 CFR Part 11 / Annex 11 compliance checks

# 5. Project Schedule

| Milestone | Target Date | Owner |
| --- | --- | --- |
| Project kick-off and plan approval | 2026-05-01 | PM |
| System Criticality Assessment complete | 2026-05-07 | VE / BQR |
| User Requirements Specification approved | 2026-05-14 | SO / BQR |
| Validation Plan approved | 2026-05-21 | VE / BQR |
| Architecture Specification approved | 2026-05-28 | IE / VE |
| Installation Qualification complete | 2026-06-04 | IE / VE |
| Test execution complete | 2026-06-18 | VE / BQR |
| Validation Report approved | 2026-06-25 | SO / BQR |
| Authorization for Use signed | 2026-06-30 | SO |

# 6. Document Deliverables

| Document | Document Number | Type |
| --- | --- | --- |
| Project Plan | CPT-VL-ISVP-PP Capalyst-001 | Planning |
| System Criticality Assessment | CPT-VL-ISVP-SCA Capalyst-001 | Planning |
| User Requirements Specification | CPT-VL-ISVP-UR Capalyst-001 | Specification |
| Validation Plan | CPT-VL-ISVP-VP Capalyst-001 | Planning |
| Architecture Specification | CPT-VL-ISVP-ArS Capalyst-001 | Specification |
| Data Migration Plan | CPT-VL-ISVP-DMP Capalyst-001 | Specification |
| Installation Qualification | CPT-VL-ISVP-IQ Capalyst-001 | Verification |
| Infrastructure & Application Operations Manual | CPT-VL-ISVP-IAOM Capalyst-001 | Verification |
| Test Report | CPT-VL-ISVP-TR Capalyst-001 | Verification |
| Database Comparison | CPT-VL-ISVP-DBC Capalyst-001 | Verification |
| Authorization for Use | CPT-VL-ISVP-AFU Capalyst-001 | Closure |
| Validation Report | CPT-VL-ISVP-VR Capalyst-001 | Closure |
| Version Release Notes Review | CPT-VL-CVP-Capalyst-v1.0.0-001 | Change Control |

# 7. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| System Owner | Hannes van der Berg |  |  |
| Business Quality Representative | Monique Leblanc |  |  |
| Validation Expert | TBD |  |  |

## Document Change History

| Version | Date | Description | Author |
| --- | --- | --- | --- |
| 1.0 | 2026-06-01 | Initial approved version | Validation Team |